## Cover
MANAGEMENT ACTION PLAN
DRAFT
(Pending approval by ad-hoc Oversight Committee of the Global Fund's Board)

## Overview
Link between challenges identified in IOS report, actions outlined in the Management Response and Work Plan
This overview sheet is to enable clear tracking of the actions approved in the Management Reponse with those listed in the detailed work plan.
It should be read side-by-side with the Management Response.
Challenges Identified in IOS Report and/or Management Response | Analysis of contributing factors | Proposed Areas of Action as outlined in Management Response |  | Work Plan Listing
Contracts and Payments
1). Failures in compliance with the Global Fund Policy on Secretariat Procurement of Goods and Services (e.g. contracts awarded on a non-competitive base, without the appropriate CRC approval and/or where work commenced prior to a contract being in place). Appropriate documentation not always available. 2). Questions whether certain activities that resulted in payments from Global Fund bank accounts were adequately governed by policy and were outside WHO requirements and practices. | a) Insufficient forward planning, monitoring tools and oversight of contracting pipeline | * Strengthen management oversight and systems | Develop and implement enhanced contracts database | A1
| b) Lack of clear guidance and staff awareness regarding contracting policies/procedures and responsibilities | * Enhance and document internal policies and procedures | Thorough review of GF and WHO procurement policies | A2
| c) Low resourcing and capacity in contracting team d) Log of exceptions to the Administrative Services Agreement between WHO and the Global Fund requires updating and greater clarity regarding the nature of matters that require an exception to be agreed and logged e) Tension between needs of a start-up organization focused on rapid response and policy framework of WHO |  | Revision of guidelines for credit card holders to give expanded guidance relating to ‘exceptional’ rather than ‘emergency’ use | A3
|  |  | Preparation of detailed policies for activities that give rise to payments from GF bank accounts | A4
|  |  | Ongoing recording of all exceptions to WHO rules | A5
|  |  | Exploration of contract fast-tracking possibilities | A6
|  | * Strengthen training for management and staff | Institute regular training courses on contracting policies and procedures | A7
|  |  | Publish a GF contracting and procurement manual | A8
|  | * Ensure appropriate staff capacity and structures | Continue strengthening the contracts team Ensure clear performance targets and management | A9 A10
3). Discrepancies in two APW documents |  | * Referred to IG's office |  |  | Overaching Measure
|  | Recruitment |  |  | * Organization-wide accountability framework including clarification of roles and responsibilities
1) Insufficient transparency in recruitment of short-term staff and in some cases extension of contracts without proper selection process 2) Questions with regard to direct appointments 3) Lack of clarity around secondment and lines of accountability 4) Failure in compliance with WHO Staff rules in relation to payments | a) Underresourced HR team b) Non comprehensive Human Resource Strategy c) Lack of supporting systems/tools for forward planning of HR needs, pipeline management and oversight d) WHO policy on short term and direct appointments too high level to provide clear standards, roles and accountabilities e) Insufficient awareness of staff on recruitment policies, roles and responsibilities | * Strengthen management oversight and systems | Develop and implement enhanced HR database and management tool | B1
|  | * Enhance and document internal policies and procedures | Establish clearer policy for direct appointments | B2
|  |  | Establish a review panel for direct appointments | B3
|  |  | Establish clear policies for recruitment of short-term staff | B4
|  | * Strengthen training for management and staff | Develop and implement an HR training module | B5
|  |  | Integrate briefing sessions on recruitment into staff induction | B6
|  |  | Distribute a summary and checklist of recruitment guidelines to all staff | B7
|  | * Ensure appropriate staff capacity and structures | Strengthen the HR team | B8
Involvement of Family Members
1) Finding of pro-bono involvement of a family member in GF activities | a) Insufficient clarity and stringency of WHO policies and guidelines on non-employment/ employment involvement of family members for small organization like the GF | * Enhance, document and enforce internal policies and procedures on involvement of family members | Develop and implement comprehensive guidelines on the involvement of family members | C1

## Contracts
Work Plan for Contracting Actions
Objective: Strengthen the contracting function to effectively and efficiently support the needs of the Global Fund
and ensure all contracts are awarded in line with WHO/Global Fund procesess
Oversight: Contracts Steering Group (Christoph Benn, Mike Marchment, Helen Evans, and Barry Greene. Chaired by Helen Evans)
MR Action | Action | Specific Steps | Completion Date | Status and Comments
A9, A10 | 1. Clarify contracting processes, roles and responsibilities and strengthen the Contracts Team, including performance management | 1. Mapping of contracting functions completed | Complete | Business mapping of contracting function and options for future organizational arrangements completed by consultants and presented to and discussed by Contracts Steering Group. Final decision on contracting model made based on this analysis
|  | 2. Options paper on organizational contracting model and roles/ responsibilities prepared | Complete
|  | 3. Decisions on organizational contracting model finalized | Complete
|  | 4. Interim team design, leadership, and performance indicators agreed | 2006-03-20 | Initial team design and leadership completed and development of performance objectives begun with head of general contracts team
|  | 5. Recruitment launched | 2006-03-24 | Recruitment of one position (contract specialist) launched. Job description for other position (LFA Contract Manager) in development.
|  | 6. Interview and selection | 2006-05-20
|  | 7. Enhanced team in place, including final team design | July
A1 | 2. Upgrade Contract Information Systems to support contracts management and monitoring including record keeping | 1. Definition of scope/upgrades completed together with IS | Complete | Consultant completed an analysis of needs and options for effective contracting information system. Based on that analysis, Contracts and IS teams have developed a project plan.
|  | 2. Project plan and costing for strengthening contracting IT systems prepared | Complete
|  | 3. Initial design completed and pilot testing - Feedback collected & integrated | June | A scope of work is expected to be completed by 24th of April. Meanwhile discusssions have started with WHO who have a new IS project team . We have approached this project team to give us a timescale and cost for development of the CIS once the scope of work is completed. As a contingency, a full RFP is being developed.
|  | 4. Fully operational | July-August
|  | 5. On going training | August onwards
A2, A6 | 3. Clarify GF procurement policy and align with WHO contracting policies | 1. GF proposal of changes developed | Complete | Global Fund Legal conducted review of potential differences and changes.
|  | 2. Review completed, including consultations and agreement with WHO | 31-Mara | Document of proposed policy alignment produced and shared with WHO. Two meetings held with WHO. Likely completion date before 31 May.
|  | 3. FAC update | Complete | Update on current progress provided to FAC on Mar.23
|  | 4. Finalized version agreed and provided to FAC | Next appropriate FAC meeting
|  | 5. Ongoing training | May onwards
A8, A7 | 4. Produce a Manual on Contracting Policies and Procedures and Associated Training Module | 1. Consultant selected | 2006-03-13 | Quotes from 3 consultants obtained. Selection panel currently considering options. It is important that GF procurement policy be agreed with WHO before manual drafting begins in earnest
|  | 2. Manual drafted & circulated | 2006-07-15
|  | 3. Feedback collected & analysed | 2006-07-31
|  | 4. Final version published | 2006-08-10
|  | 5. Trainining module designed | 2006-08-17
|  | 6. Module incorporated into induction and ongoing training | August onwards
a -- Expected completion date now 31 May.

## Finance - LOE
Work Plan for Finance Actions
Objective: Ensure guidelines for the use of Global Fund bank accounts and credit cards are clearly documented and communicated
Oversight: CFO, CAO
MR Action | Action | Specific Steps | Completion Date | Status and Comments
A3 | 1. Revise GF Credit Card Guidelines | 1. Amend the guidelines to give expanded guidance on usage and who holds cards | Complete | Completed on 10 February and approved by FAC on 23 March.
|  | 2. Re-issue guidelines to cardholders | Complete | Completed on 10 February 2006
A4 | 2. Document detailed guidelines to codify practices on activities paid from Global Fund Credit Suisse Account | 1. Develop user guidelines for: relocation services, refundable advances, support for external studies by staff, miscellaneous allowances to staff, office catering & hospitality, travel and meeting expenses (not covered by WHO), miscellaneous purchases. | 2006-03-17 | Near-complete draft reviewed by FAC on 23 March is in line with FAC expectations; will be completed by 15 May.
| 3. Review internal controls for operating expense payments | 1. Review list of authorized signatories and amend if necessary to provide appropriate division of duties | 2006-03-31 | Draft compiled; will be finalized by 21 April.
|  | 2. Review payments mentioned in IOS Report as being non-compliant with financial rules to identify and eliminate any control gaps | 2006-03-31 | Review will be completed by 31 May.
Work Plan for Log of Exceptions Actions
MR Action | Action | Specific Steps | Completion Date | Status and Comments
A5 | Ensure Ongoing Updating of the Log of Exceptions | 1. Initial discussions with WHO to define goals and identify WHO focal point | Complete | Preliminary meetings with WHO held. Legal team liasing with WHO on procedures and potential entries
|  | 2. WHO to propose general principles for determination of when an entry to the Log of Exceptions is required | Complete | Communication from WHO received March 6.
|  | 3. Discuss status of Log of Exceptions, specific entries to be added, and procedure for future logging | 2006-03-31 | First exception agreed with WHO. Discussions ongoing with WHO on other areas for Log. Likely completion in May.
|  | 4. Ensure regular updating | 31-Mar. onwards

## Human Resources
Work Plan for Human Resources Actions
Objective: Strengthen human resources practices and policies to most effectively support for the needs of the organization and ensure high levels of transparency
in this important area
Oversight: Office of the Executive Director (as of January 1, 2006, the Human Resources Unit reports ad interim to the Executive Director and Deputy Executive Director)
MR Action | Action | Specific Steps | Completion Date | Status and Comments
B8 | 1. Review and develop the HR function and strengthen the HR Team through the development of a comprehensive H.R. Strategy which will include clarification of roles and responsibilities and recruitment of new staff | 1. HR consultant recruited to assist in development of HR strategy, core systems and corresponding organizational structure | Complete | Comprehensive HR strategy , including structure and role of HR team, developed with assistance from consultant.
|  | 2. Recruitment of additional HR staff positions completed and strengthened HR team in place | June | Initial screening of business partner positions at heart of more strategic approach to HR complete. Initial screening of other positions in new HR structure also completed. Interviews to commence week of Apr. 10
B1 | 2. Strengthen HR Information Systems to support management and planning of all areas of HR | 1. Scope/modules defined | Complete | Initial analysis and options prepared by consultant. Discussions currently being held with WHO to explore making better use of its HR systems, including E-recruitment, E-training, and E-performance management. Options being explored for more extensive HR database which would fit with WHO system. Final decisions on way forward expected in May
|  | 2. Project plan and costing for strengthening Human Resources IT systems prepared | 2006-03-27
|  | 3. Initial application designed and pilot testing | April | Delayed due to continuing exploration of best solutions for HR systems.
|  | 4. First priority modules launched | May-June
B2, B3, B4 | 3. Review and strengthen/clarify where necessary recruitment processes, policies and guidelines, with a focus on policy and process for short-term staff, direct appointments, secondees and promotions | 1. Existing WHO policies and guidelines reviewed. | Complete | Existing policies and processes for short- as well as long-term staff reviewed. First draft discussed with EMT and Staff Council. Changes incorporated and final draft sent to WHO for review and inclusion in Log of Exceptions.
|  | 2. Draft of adapted processes and corresponding policy on recruitments, including direct appointment, presented to EMT and Staff Council | Complete
|  | 3. Draft policy on secondments and promotions completed and presented to EMT and Staff Council | June
|  | 4. Included in WHO Log of Exceptions if appropriate | 2006-03-27 | Final recruitment policy presented to WHO April 4. Awaiting response.
B5, B6, B7 | 4. Institute Training on Recruitment Policies and Procedures, including briefing sessions for new staff and distribution of recruitment guidelines to all staff. | 1. Draft training module designed | Complete | Draft training template produced.
|  | 2. Training launched, recruitment guidelines developed | 2006-03-27 | Awaiting final agreement of recruitment policies with WHO
|  | 3. Integrated into induction | 2006-04-03
Work Plan for Involvement of Family Members Actions
C1 | 1. Develop Comprehensive Guidelines on Family Members, Partners and Spouse Involvement* | 1. Options paper on Policy/Guidelines presented to EMT and Staff Council | Complete | DLA Piper has prepared an options paper in collaboration with HR team. Options paper reviewed, revised, and shared with WHO.
|  | 2. Presentation of options to the Ethics Committee | March/ April | Options paper and memorandum to be sent to Ethics Committee for consideration week of Apr. 10
|  | 3. Action plan presented to Board | 2006-04-27 | Following decision by Ethics Committee and agreement with WHO
|  | 4. Integrated into induction | April onwards
* According to the descision point at the 12th Board meeting, this area of action will be reviewed and reported on by the Ethics Committee